## Sprint Data
Team Metrics
Sprint Naming Syntax - <YY.MM><S#> <ORG>-<TeamName>, Where "YY" is year, "MM" is the month and "S#" is 1, 2 or 3 depending on number of sprints in the month. <ORG> is the organization the team belongs to. |  |  |  | Example: "2019.06S1 WEB-Elephants" is the first sprint in June of 2019 for the Elephants team in the Web Apps org. "2019.10S2 EDW-Amazers" is the second sprint in October of 2019 for the Amazers team in the Enterprise Data Warehouse team.
Tigers |  | Sprint Board | <URL>
Jack Ryan |  | Team Space | <URL> |  |  |  | Planned Work |  |  |  | Unplanned Work | [5 empty] | Planned |  |  |  | Unplanned
Sprint ID | Duration (Weeks) | Start Date | End Date | Notes | Team Availability | Happiness Score | Planned Story Points | Planned PBIs | Completed Story Points | Completed PBIs | Unplanned Story Points | Unplanned PBI Count | Completed Unplanned Story Points | Completed Unplanned PBIs | Escaped Defects Found | PBI Cycle Time | Done to Plan % | Done to Planned Rolling Average | Story Points Rolling Average | Story Count Rolling Average | Story Points Rolling Average | Story Count Rolling Average | Cylce Time Rolling Average
2018.12S1 Team Tigers | 2 | 2019-12-05 | 2019-12-18 |  | 6 | 3.71 | 34 | 4 | 8 | 1 |  |  |  |  | 0 | 6 | 25% | 25% | 8 | 1 | #N/A | #N/A | 6
2018.12S2 Team Tigers | 2 | 2019-12-19 | 2020-01-01 | Holiday Sprint | 6 | 3.14 | 52 | 6 | 13 | 2 |  |  |  |  | 3 | 6 | 33.33% | 29.17% | 11 | 2 | #N/A | #N/A | 6
2019.01S1 Team Tigers | 2 | 2020-01-02 | 2020-01-15 |  | 6 | 2.9 | 54 | 7 | 38 | 5 |  |  |  |  | 4 | 5.63 | 71.43% | 43.25% | 20 | 3 | #N/A | #N/A | 5.8767
2019.01S2 Team Tigers | 2 | 2020-01-16 | 2020-01-29 |  | 6 | 3.1 | 92 | 12 | 68 | 8 |  |  |  |  | 10 | 2.33 | 66.67% | 57.14% | 40 | 4 | #N/A | #N/A | 4.6533
2019.02S1 Team Tigers | 2 | 2020-01-30 | 2020-02-12 |  | 6 | 3.4 | 112 | 14 | 54 | 7 |  |  |  |  | 6 | 2.76 | 50% | 62.7% | 53 | 6 | #N/A | #N/A | 3.5733
2019.02S2 Team Tigers | 2 | 2020-02-13 | 2020-02-26 | John clark on vacation | 6 | 3.6 | 84 | 10 | 63 | 8 |  |  |  |  | 2 | 3.71 | 80% | 65.56% | 62 | 7 | #N/A | #N/A | 3.6075
2019.03S1 Team Tigers | 2 | 2020-02-27 | 2020-03-11 |  | 6 | 3.9 | 86 | 11 | 81 | 10 |  |  |  |  | 1 | 3.5 | 90.91% | 73.64% | 66 | 8 | #N/A | #N/A | 3.075
Do Not Erase Cells. To add a new row, Copy and Paste the immediate previous Row
Lions |  | Sprint Board | <URL>
Jane Foster |  | Team Space | <URL> |  |  |  | Planned Work |  |  |  | Unplanned Work | [5 empty] | Planned |  |  |  | Unplanned
Sprint ID | Duration (Weeks) | Start Date | End Date | Notes | Team Availability | Happiness Score | Planned Story Points | Planned PBIs | Completed Story Points | Completed PBIs | Unplanned Story Points | Unplanned PBI Count | Completed Unplanned Story Points | Completed Unplanned PBIs | Escaped Defects Found | PBI Cycle Time | Done to Plan % | Done to Planned Rolling Average | Story Points Rolling Average | Story Count Rolling Average | Story Points Rolling Average | Story Count Rolling Average | Cylce Time Rolling Average
2018.12S1 Team Lions | 2 | 2019-12-05 | 2019-12-18 |  | 5 | 3 | 39 | 4 | 5 | 1 |  |  |  |  | 0 | 6 | 25% | 25% | 5 | 1 | #N/A | #N/A | 6
2018.12S2 Team Lions | 2 | 2019-12-19 | 2020-01-01 | Holiday Sprint | 5 | 3 | 57 | 7 | 18 | 3 |  |  |  |  | 4 | 6 | 42.86% | 33.93% | 12 | 2 | #N/A | #N/A | 6
2019.01S1 Team Lions | 2 | 2020-01-02 | 2020-01-15 | Sif out half sprint | 5 | 2 | 63 | 8 | 13 | 1 |  |  |  |  | 5 | 5.25 | 12.5% | 26.79% | 12 | 2 | #N/A | #N/A | 5.75
2019.01S2 Team Lions | 2 | 2020-01-16 | 2020-01-29 | Loki on vacation, Heimdall fixing the Bifrost | 5 | 2.25 | 58 | 8 | 32 | 5 |  |  |  |  | 3 | 5.25 | 62.5% | 39.29% | 21 | 3 | #N/A | #N/A | 5.5
2019.02S1 Team Lions | 2 | 2020-01-30 | 2020-02-12 | Heimdall fixing the Bifrost | 5 | 2.8 | 115 | 15 | 67 | 8 |  |  |  |  | 6 | 5.96 | 53.33% | 42.78% | 37 | 4 | #N/A | #N/A | 5.4867
2019.02S2 Team Lions | 2 | 2020-02-13 | 2020-02-26 |  | 5 | 3.2 | 97 | 13 | 82 | 10 |  |  |  |  | 2 | 3.25 | 76.92% | 51.31% | 60 | 6 | #N/A | #N/A | 4.9275
2019.03S1 Team Lions | 2 | 2020-02-27 | 2020-03-11 |  | 5 | 3.65 | 65 | 9 | 60 | 8 |  |  |  |  | 1 | 3.21 | 88.89% | 70.41% | 70 | 8 | #N/A | #N/A | 4.4175
Do Not Erase Cells. To add a new row, Copy and Paste the immediate previous Row
Yellow Brick Road Product |  | Agile Board | <URL>
|  | Team Space | <URL> |  |  |  | Planned Work |  |  |  | Unplanned Work | [5 empty] | Planned |  |  |  | Unplanned
Sprint ID | Duration (Weeks) | Start Date | End Date | Notes |  | Combined Happiness Score | Combined Planned Story Points | Combined Planned PBIs | Compbined Completed Story Points | Combined Completed PBIs | Unplanned Story Points | Unplanned PBI Count | Completed Unplanned Story Points | Completed Unplanned PBIs | Escaped Defects Found | PBI Cycle Time | Done to Plan % | Done to Planned Rolling Average | Story Points Rolling Average | Story Count Rolling Average | Story Points Rolling Average | Story Count Rolling Average | Cylce Time Rolling Average
2018.12S1 YellowBrick | 2 | 2019-12-05 | 2019-12-18 |  |  | 3.355 | 73 | 8 | 13 | 2 | 0 | 0 | 0 | 0 | 0 | 6 | 25% | 25% | 13 | 2 | #N/A | #N/A | 6
2018.12S2 YellowBrick | 2 | 2019-12-19 | 2020-01-01 |  |  | 3.07 | 109 | 13 | 31 | 5 | 0 | 0 | 0 | 0 | 7 | 6 | 38.46% | 31.73% | 22 | 4 | #N/A | #N/A | 6
2019.01S1 YellowBrick | 2 | 2020-01-02 | 2020-01-15 |  |  | 2.45 | 117 | 15 | 51 | 6 | 0 | 0 | 0 | 0 | 9 | 5.44 | 40% | 34.49% | 32 | 4 | #N/A | #N/A | 5.8133
2019.01S2 YellowBrick | 2 | 2020-01-16 | 2020-01-29 |  |  | 2.675 | 150 | 20 | 100 | 13 | 0 | 0 | 0 | 0 | 13 | 3.79 | 65% | 47.82% | 61 | 7 | #N/A | #N/A | 5.3075
2019.02S1 YellowBrick | 2 | 2020-01-30 | 2020-02-12 |  |  | 3.1 | 227 | 29 | 121 | 15 | 0 | 0 | 0 | 0 | 12 | 4.36 | 51.72% | 48.8% | 91 | 10 | #N/A | #N/A | 5.118
2019.02S2 YellowBrick | 2 | 2020-01-30 | 2020-02-12 |  |  | 3.4 | 181 | 23 | 145 | 18 | 0 | 0 | 0 | 0 | 4 | 3.48 | 78.26% | 54.69% | 122 | 13 | #N/A | #N/A | 4.845
2019.03S1 YellowBrick | 2 | 2020-02-13 | 2020-02-26 |  |  | 3.775 | 151 | 20 | 141 | 18 | 0 | 0 | 0 | 0 | 2 | 3.355 | 90% | 65% | 136 | 16 | #N/A | #N/A | 4.4042
Do Not Erase Cells. To add a new row, Copy and Paste the immediate previous Row
Formulas:
End Date = [Team Space]+13
Team Space = [End Date, row above]+1

## Instructions
Team Metrics Template |  |  | Created by: Joel Bancroft-Connors (TheGorillaCoach.com)
Creative Commons 3.0- Attribution
Sprint Data Worksheet
Column | Use | Instructions | Notes
A & C (Row 3-4)- Team Info | In these cells enter the name of the team (A3), the Scrum Master (A4), a link to the teams electronic board (C3) and to their electronic team space (C4), e.g. Confluence, if they have one. | During initial setup, of this document, enter the Scrum Team name, Scrum Master and relevant URLs. | You will need to repeat this for every team being tracked. For example, rows 3 and 4 are for Team Tigers. Rows 14 and 15 are for Team Lions.
A & C (Row 25-34)- Multi-Team Tracking | For aggregating multiple teams into a single view. | Delete if only tracking one team or if each team is working on a separate product. Data is automatically pulled from the team sections above. (Note: If three or more teams are being tracked, the formulas in columns G28 to Q34 will need to be manually updated to reflect the new teams). | Used primarily when multiple teams are working from the same product backlog. Allows the display of aggregate data, as shown in the YellowBrick Aggreate Worksheet.
A- Sprint Naming (ID) | Column A is for tracking the unique Sprint Name (ID) for each individual Sprint. | At the start of a new Sprint, insert a new row below the last Sprint tracked (Row 12 in the example data). Copy and paste the row above, so as to capture all the formulas. Clear the Data from Columns E, and G-Q. Replace the Sprint ID with the current Sprint ID based on the naming convention at the top of the Sprint Data Worksheet. Enter the Scrum Teams Forecasted Sprint Points and PBI count in Columns H and I respectively. | Sprint Numbering: If a Sprint crosses the start of a new month, number the sprint based on which month the most days fall in. For example, a sprint that starts on Jan 29, would be the first sprint of February (e.g. 02S1) and a Sprint that ends on March 3 would be considered a February Sprint (e.g. 02S2).
B- Weeks | Tracks the duration of the Sprint in weeks. | Enter a value between 1 and 4. | Sprints over two weeks in length are not recommended for most products and projects.
C- Start | Tracks the date your sprint starts. | You only need to enter a value in the first Sprint (e.g. C6). The forumulas will do the rest of the work for future Sprints. | The Column C formula is =D6+1. In the example, the first Sprint ended on Dec 18. The next Sprint started on Dec 19.
D- End | The date your sprint ends. | This date will auto calculate based on the start date and the Sprint duration (Column B). | The Column D formula is defaulted for a two week Sprint (=C6+13). For a one week Sprint the forumla would be =C6+6
E- Notes | Used to track notes related to the Sprint such as vacations, major impediments, etc. | Free form text for your notes. | If you are using the Team Availability sheet, it can be useful to copy the notes from this sheet to here for a complete record.
F- Team Availability | Tracks the team's Availability. | Basic usage is to list the size of the Development Team. Advanced usage is to list a decimal number representing the team's availability based on their full strength minus absences, holidays and non-Sprint work. | Advanced Usage: This is used for Sprint Planning. If your team has and average velocity of 50 story points and half the team is out for the sprint, you can't still be expected to do 50 points. In this example, the Availability would be 0.5 and you would multiply the velocity by this to get a suggested Sprint forecast of 25 points.
G- Happiness Score | Tracks Team Happiness Score (a measure of Stability.) | Enter the Happiness Score collected during the Retrospective. | We recommended using the full Crisp Happiness Survey via an automatic survey tool. Send this out prior to the Sprint Retrospective and used the results as part of the Gathering Data stage of the Retrospective.
H- Planned Story Points | Lists the amount of Story Points the team forecasted during Sprint Planning. | Enter this data at the completion of Sprint Planning based on the team's forecast.
I- Planned PBI | Lists the amount of Product Backlog Items the team forecasted during Sprint Planning. | Enter this data at the completion of Sprint Planning based on the team's forecast. | It is useful to track both Story Points and PBIs. Having both allows for improved forecasting during Sprint Planning. For example, a team with a velocity of 50 story points and 10 PBI, decides to take on 60 story points and 9 PBI. This is over their story point velocity and under their PBI velocity so is likely only a small risk. If, instead, they chose to do 60 story points and 20 PBI a Scrum Master might observe that this is well beyond the PBI count they have ever done and that while each PBI is smaller, the context switching might make it hard to complete all the work.
J- Completed Story Points | Lists the number of story points the team completed at the end of the Sprint. | Enter this data from the Scrum Team's physical board or online tool. Only enter points for work that reached Done. | Note on changing estimates: Use the original Story Points estimated for the work.
K- Completed PBIs | Lists the number of Product Backlog Items that reached Done. | Enter this data from the Scrum Team's physical board or online tool. Only enter points for work that reached Done.
L- Unplanned Story Points | Used to track Story Points of work that was added to the Sprint after Sprint Planning. | Enter this data from the Scrum Team's physical board or online tool. Only enter points for work that reached Done. | If your teams are not regularily having worked added after Sprint Planning, feel free to hide columns L through O. Theses columns are useful for Scrum Teams that are seeing heavy interupts or are adding work of their own to the Sprint.
M- Unplanned PBI | Used to track Product Backlog Items that were added to the Sprint after Sprint Planning. | Enter this data from the Scrum Team's physical board or online tool. Only enter points for work that reached Done.
N- Completed Unplanned Story Points | Lists the number of story points the team completed at the end of the Sprint. | Enter this data from the Scrum Team's physical board or online tool. Only enter points for work that reached Done. | Note on changing estimates: Use the original Story Points estimated for the work.
O- Completed Unplanned PBIs | Lists the number of Product Backlog Items that reached Done. | Enter this data from the Scrum Team's physical board or online tool. Only enter points for work that reached Done.
P- Escaped Defects | Lists the number of Escaped Defects reported against the Team during this Sprint. | Enter this value from the relevant data. | Escaped Defect: Any issue found in the previous Product Increment regardless of the reporter (internal, customer, partner, etc). Issues found during the Sprint are not considered Escaped Defects as the team and the Product Owner knew about them and either fixed them or chose to put them in the Product Backlog for later work. Tracking Note: The first Sprint will always be zero. Escaped Defects are specifically against work done by the Scrum Team, in a previous Sprint. Issues found from prior to the team moving to Scrum should be tracked seperately, for example as a "legacy bug".
Q- Cycle Time | Tracks the time it, on average, for one PBI to move from "In Progress" to "Done". | Enter this data from the relevant tracking mechanism. Always enter this as a decimal value. If the tracking mechanism reports in hours, there is an hour to decimal calculator at the bottom on this page (Cell E29). | Cycle Time is available in a number of ways and most online lifecycle management tools have a way to easily extract this. Jira Exampe: Use the Control Chart in the Sprint Reports section. 1 - Scroll to the bottom and set the dates to match those of the sprint. 2- Select the appropriate issues types (typically just Story). 3- Select the appropriate Workflow states (e.g. In Progress, Review, Block, Done). 4- Scroll to the top of the report and look at the Median number. 5- Convert this to a decimal number and use this in Column Q.
Columns R-X Blue Cells | Formulas used for generating the Charts in the Measures and Planning worksheets. | These cells are automatically populated based on the dates entered in Columns A-K. Do not enter data or erase cells, even if they look blank. To add a new row, copy the row immediately above. | Note: The first two rows have modified formulas for the rolling averages. Be sure to never copy over these rows with data from lower rows or the trending charts will become innacurate.
Corrupted Cells | If Columns R-X become corrupted. | If, at any point, cells in Columns R-X become corrupted, scroll down in this sheet and copy the formula block (Cell K29). Paste it starting in the top right cell (R6 normally). To fix additional rows beyond the first 8, copy and paste the last row (L14 normally).
Tracking "Are We Done Yet?" | To track the progress of an Epic, Feature or Project you will need to use a Burn Up Chart or use a Forecasting Tool.
Date Calculator | Use the tool to the right to convert hours into dates. Useful when pulling cycle time from an electronic system. |  |  | Days Calculator |  |  |  |  | Planned |  |  |  | Unplanned
|  |  |  | Weeks | Days | Hours | Days Result |  | Done to Plan % | Done to Planned Rolling Average | Story Points Rolling Average | Story Count Rolling Average | Story Points Rolling Average | Story Count Rolling Average | Cylce Time Rolling Average
|  |  |  | 0 | 3 | 17 | 3.7083 |  | 0% | 0% | #N/A | #N/A | 17 | 4 | #N/A
|  |  |  | Don't change the colored cells |  |  |  |  | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A
[9 empty] | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A
[9 empty] | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A
|  |  |  | Hours | Decimal |  | Weeks | Days | 0% | 0% | #N/A | #N/A | #N/A | #DIV/0! | #N/A
|  |  |  | 1 | 0.04 |  | 1 | 7 | 0% | 0% | #N/A | #N/A | #N/A | 1 | #N/A
|  |  |  | 2 | 0.08 |  | 2 | 14 | 0% | 0% | #N/A | #N/A | #N/A | 2 | #N/A
|  |  |  | 3 | 0.13 |  | 3 | 21 | Do Not Erase Cells. To add a new row, Copy and Paste the immediate previous Row
|  |  |  | 4 | 0.17 |  | 4 | 28
|  |  |  | 5 | 0.21 |  | 5 | 35
|  |  |  | 6 | 0.25 |  | 6 | 42
|  |  |  | 7 | 0.29 |  | 7 | 49
|  |  |  | 8 | 0.33 |  | 8 | 56
|  |  |  | 9 | 0.38 |  | 9 | 63
|  |  |  | 10 | 0.42 |  | 10 | 70
|  |  |  | 11 | 0.46 |  | 11 | 77
|  |  |  | 12 | 0.5 |  | 12 | 84
|  |  |  | 13 | 0.54 |  | 13 | 91
|  |  |  | 14 | 0.58
|  |  |  | 15 | 0.63
|  |  |  | 16 | 0.67
|  |  |  | 17 | 0.71
|  |  |  | 18 | 0.75
|  |  |  | 19 | 0.79
|  |  |  | 20 | 0.83
|  |  |  | 21 | 0.88
|  |  |  | 22 | 0.92
|  |  |  | 23 | 0.96
|  |  |  | 24 | 1

## Deliverable Tracking (hidden)
Deliverables | Weeks | Start | End | Notes | Deliverables | Story Count | Defect Count | Bug Count | Incomplete Work | All Item Cycle Time | Story Cycle Time | Defect Cyle Time | Bug Cycle Time | Planned Work items | Value Work Items Completed | Total Work Items Completed | Deliverables per Month | Workitems Per Week | Stories Per Week | Defects Per Week | Bugs per Week | Done to Plan % | Defects Time (Wks) | Bug Time (Wks) | Defect Time Rolling Average | Bug Time Rolling Average | Deliverables/ Month Rolling Average | Average Stories per Deliverable | Work Items Rolling Average | Stories/Week Rolling Average | Defects/Week Rolling Average | Bugs/Week Rolling Average | All Item Cycle Rolling Average | Story Cycle Rolling Average | Defect Cycle Rolling Average | Bug Cycle Rolling Average | QA | Dev | Team Size | Efficiency WIpM/TS | Efficiency (Stories per person per week)
One Video 2015 | 35 | 2015-06-01 | 2015-12-31 |  | 123 | #REF! | #REF! | #REF! | #REF! | 6.96 | 11.08 | 3.08 | 6.17 | #REF! | #REF! | #REF! | 14.0571 | #REF! | #REF! | #REF! | #REF! | 0% | #REF! | #REF! | #DIV/0! | #DIV/0! | 13.6638 | #REF! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.7367 | 4.25 | 1.21 | 2.6233 |  |  | 59.4444 |  | 1.1765
Display 2015 | 35 | 2015-06-01 | 2015-12-31 |  | 35 | #REF! | #REF! | #REF! | #REF! | 8.25 | 8.54 | 6 | 9.13 | #REF! | #REF! | #REF! | 4 | #REF! | #REF! | #REF! | #REF! | 0% | #REF! | #REF! |  |  | 4.0912 | #REF! | [10 empty] | 16.2778 |  | 0
Supply 2015 | 35 | 2015-06-01 | 2015-12-31 |  | 45 | #REF! | #REF! | #REF! | #REF! | 9.5 | 14.88 | 4.21 | 6 | #REF! | #REF! | #REF! | 5.1429 | #REF! | #REF! | #REF! | #REF! | 0% | #REF! | #REF! |  |  | 4.9345 | #REF! | [10 empty] | 23.8333 |  | 0
Infrastructure 2015 | 35 | 2015-06-01 | 2015-12-31 |  | 43 | #REF! | #REF! | #REF! | #REF! | 4.54 | 6.75 | 2 | 3.96 | #REF! | #REF! | #REF! | 4.9143 | #REF! | #REF! | #REF! | #REF! | 0% | #REF! | #REF! |  |  | 4.6382 | #REF! |  |  |  |  | 2.7367 | 4.25 | 1.21 | 2.6233 |  |  | 19.3333 |  | 1.1765
One Video Q2 2015 | 9 | 2015-06-15 | 2015-06-30 |  | 23 | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | 10.2222 | #REF! | #REF! | #REF! | #REF! | 0% |  |  | #DIV/0! | #DIV/0! | 10.2222 |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 |  |  | 40.6667
One Video Q3 2015 | 13 | 2015-07-01 | 2015-09-30 |  | 58 | #REF! | #REF! | #REF! | #REF! | 6.83 | 11.92 | 2.83 | 6.25 | #REF! | #REF! | #REF! | 17.8462 | #REF! | #REF! | #REF! | #REF! | 0% | #REF! | #REF! | #DIV/0! | #DIV/0! | 14.0342 |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.605 | 1.54 | 0.355 | 2.395 |  |  | 60.6667 |  | 3.2468
One Video Q4 2015 | 13 | 2015-10-01 | 2015-12-31 |  | 42 | #REF! | #REF! | #REF! | #REF! | 6.96 | 10.88 | 3.25 | 6.13 | #REF! | #REF! | #REF! | 12.9231 | #REF! | #REF! | #REF! | #REF! | 0% | #REF! | #REF! | #DIV/0! | #DIV/0! | 13.6638 |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.7367 | 4.25 | 1.21 | 2.6233 |  |  | 77 |  | 1.1765
Display Q2 2015 | 9 | 2015-06-15 | 2015-06-30 |  | 11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 4.8889 | #REF! | #REF! | #REF! | #REF! | 0% | #REF! | #REF! |  |  | 4.8889 | [6 empty] | 0 |  |  |  |  | 13.6667
Display Q3 2015 | 13 | 2015-07-01 | 2015-09-30 |  | 16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 4.9231 | #REF! | #REF! | #REF! | #REF! | 0% | #REF! | #REF! |  |  | 4.906 | [11 empty] | 15.6667 |  | 0
Display Q4 2015 | 13 | 2015-10-01 | 2015-12-31 |  | 8 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 2.4615 | #REF! | #REF! | #REF! | #REF! | 0% | #REF! | #REF! |  |  | 4.0912 | [11 empty] | 19.5 |  | 0
Supply Q2 2015 | 9 | 2015-06-15 | 2015-06-30 |  | 7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 3.1111 | #REF! | #REF! | #REF! | #REF! | 0% | #REF! | #REF! |  |  | 3.1111 | [11 empty] | 18
Supply Q3 2015 | 13 | 2015-07-01 | 2015-09-30 |  | 20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 6.1538 | #REF! | #REF! | #REF! | #REF! | 0% | #REF! | #REF! |  |  | 4.6325 | [11 empty] | 22 |  | 0
Supply Q4 2015 | 13 | 2015-10-01 | 2015-12-31 |  | 18 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 5.5385 | #REF! | #REF! | #REF! | #REF! | 0% | #REF! | #REF! |  |  | 4.9345 | [11 empty] | 31.5 |  | 0
Infrastructure Q2 2015 | 9 | 2015-06-15 | 2015-06-30 |  | 5 | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | 2.2222 | #REF! | #REF! | #REF! | #REF! | 0% |  |  |  |  | 2.2222 | [5 empty] | 0 | 0 | 0 | 0 |  |  | 9
Infrastructure Q3 2015 | 13 | 2015-07-01 | 2015-09-30 |  | 22 | #REF! | #REF! | #REF! | #REF! | 3.21 | 3.08 | 0.71 | 4.79 | #REF! | #REF! | #REF! | 6.7692 | #REF! | #REF! | #REF! | #REF! | 0% | #REF! | #REF! |  |  | 4.4957 | [5 empty] | 1.605 | 1.54 | 0.355 | 2.395 |  |  | 23 |  | 3.2468
Infrastructure Q4 2015 | 13 | 2015-10-01 | 2015-12-31 |  | 16 | #REF! | #REF! | #REF! | #REF! | 5 | 9.67 | 2.92 | 3.08 | #REF! | #REF! | #REF! | 4.9231 | #REF! | #REF! | #REF! | #REF! | 0% | #REF! | #REF! |  |  | 4.6382 | [5 empty] | 2.7367 | 4.25 | 1.21 | 2.6233 |  |  | 26 |  | 1.1765
Display June | 4 |  |  |  | 4 | [33 empty] | 9
Display July | 5 |  |  |  | 7 | [33 empty] | 9
Display August | 4 |  |  |  | 5 | [33 empty] | 16
Display September | 5 |  |  |  | 7 | [33 empty] | 16
Display October | 4 |  |  |  | 4 | [33 empty] | 15
Display November | 4 |  |  |  | 3 | [33 empty] | 14
Display December | 5 |  |  |  | 5 | [33 empty] | 25
Display January | 4
Supply June | 4 |  |  |  | 1 | [33 empty] | 16
Supply July | 5 |  |  |  | 6 | [33 empty] | 20
Supply August | 4 |  |  |  | 3 | [33 empty] | 20
Supply September | 5 |  |  |  | 6 | [33 empty] | 21
Supply October | 4 |  |  |  | 11 | [33 empty] | 25
Supply November | 4 |  |  |  | 6 | [33 empty] | 30
Supply December | 5 |  |  |  | 12 | [33 empty] | 33
Supply January | 4
Infrastructure June | 4 |  |  |  | 0 | [33 empty] | 0
Infrastructure July | 5 |  |  |  | 5 | [33 empty] | 18
Infrastructure August | 4 |  |  |  | 5 | [33 empty] | 18
Infrastructure September | 5 |  |  |  | 8 | [33 empty] | 22
Infrastructure October | 4 |  |  |  | 9 | [33 empty] | 29
Infrastructure November | 4 |  |  |  | 8 | [33 empty] | 25
Infrastructure December | 5 |  |  |  | 8 | [33 empty] | 27
Infrastructure January | 4

## Velocity Predictions (hidden)
SFDC
| Points per Month |  | Month | Week |  | Number of Velocity Observations | nth Velocity Observation
Last 10 Sprints Velocity Data sorted by size | 42.5 |  |  |  | 10 data points - use 3rd from top and bottom | 5 | 1
| 64.5 |  |  |  |  | 8 | 2
| 67 | 90% Confidence Level | 67 | 16.75 | Almost certain to get here | 11 | 3
| 74.5 |  |  |  |  | 13 | 4
| 77 |  | 78.25 | 19.5625 | At our median velocity we will land here | 16 | 5
| 79 |  |  |  |  | 18 | 6
| 81 |  |  |  |  | 21 | 7
| 89.5 |  | 89 | 22.25 | This is the most we could plan for | 23 | 8
| 91 |  |  |  |  | 26 | 9
121.5
IBW
| Points per Month |  | Month | Week
Last 16 Sprints Velocity Data sorted by size | 10.5 |  |  |  | 16 data points - use 5th from top and bottom
14
24
30
| 34 | 90% Confidence Level | 34 | 8.5 | Almost certain to get here
35.5
36
| 37 |  | 39.5 | 9.875 | At our median velocity we will land here
40
44
45
| 45 |  | 45 | 11.25 | This is the most we could plan for
45
45.5
45.5
47
| 19 | 4.75
| 21.32 | 5.33
| 22.68 | 5.67
| 30 | 7.5
| 30.68 | 7.67
| 32 | 8
| 33.32 | 8.33
| 34 | 8.5
| 35 | 8.75
| 36 | 9
| 38.68 | 9.67
| 42.68 | 10.67
| 45.32 | 11.33
| 46 | 11.5
| 46 | 11.5
| 46.68 | 11.67
#VALUE! | 51 | 12.75 |  |  | 19
#VALUE! | 53 | 13.25 |  |  | 30
#VALUE! | 54 | 13.5 |  |  | 33
#VALUE! | 58 | 14.5 |  |  | 46
#VALUE! | 65 | 16.25 |  |  | 51
#VALUE! | 69.32 | 17.33 |  |  | 54
#VALUE! | 76 | 19 |  |  | 65
#VALUE! | 82.52 | 20.63 |  |  | 82
#VALUE! | 83 | 20.75 |  |  | 83
#VALUE! | 86.4 | 21.6 |  |  | 86
#REF!
#REF!